| Our School Improvement Plan - Numeracy |  |
| --- | --- |
| Summary of main strengths as identified in last SSE on (specify date): | - A strong ethos of staff planning and teaching collaboratively as evidenced by the amount of team teaching, in-class support and station teaching that is happening in our school. - Mathematic attainment is improving in line with national norms as evidenced by analysis of standardised test scores. |
| Summary of main areas requiring improvement as identified in last SSE: | - Early intervention was prioritised following analysis of previous years Sigma-T results. Children were not progressing as steadily as in literacy. - Differentiation - Assessment - teacher designed tests - Problem Solving - Mental Maths: Recall of basic facts - Use of textbooks |
| Improvement targets (related to pupils’ achievement) | - Improve pupils’ attainment in mathematics - Recall of basic number facts - Problem-solving |
| Required actions (related to teaching and learning that will help to achieve the targets) | - Target classes for in-class support and station teaching in Mathematics - Assessment of Mathematics - Teaching of problem solving skills - Use a variety of approaches with specific emphasis on Mata sa Rang without the use of a maths class textbook - To explicitly teach mathematical language in a systematic way in all classes - To support the parents in helping their children to learn mathematics |
| Persons responsible | Class teachers SEN teachers Principal Parents |
| Timeframe for action | 2014-2015 |
| Success criteria / measurable outcomes | Children’s disposition Feedback from parents Standardised test results |
| Review dates | September 2015 |

Numeracy Improvement Plan

2011-2014

Early intervention plan for Senior Infants was prioritised following analysis of previous years Sigma-T results. Children were not progressing as steadily as in literacy.

2011-2012:

- Differentiated  resources and games were created for Senior Infants

- Each child was tested at the end of Junior Infants and grouped accordingly

Action Plan 2012-2013:

Senior Infants: Power Hour September – Dec Rotated among 4 Senior Infant Classes in blocks of 2 weeks

2 Learning Support Teachers/Class Teacher / Classroom Assistant

January 2013 – Continued with one Learning Support Teacher, Classroom Assistant and Parent Volunteer

1st and 2nd Class: Station teaching: 1 session per week in each Second Class

Mental Strategies – use of adding square: Principal/3 Support Teachers/Class Teacher

Continuous Professional Development

Mata sa Rang –

C. Glennon: Learning Support Teacher Sept – Dec

- Implemented the programme in 1st Class – C. Orme Jan – April

E. Burns: Ist  Class Teacher – Implemented the programme in 1st Class  April – June

Problem Solving Workshop attended by seven teachers

Numeracy Link Training Day

Staff Meeting April 2013

Principles of Mata sa Rang were explored – E. Burns provided a summary to each teacher.

Areas for development:

Problem Solving

Mental Strategies – Adding Square- In-class support for all children in Second Class

Drumcondra Early Screening Maths Test administered to Senior Infant

- To evaluate Power Hour

- To establish areas of strengths and weaknesses

- To create differentiated groups for First Class.

2013-2014

Using the data from ESMT, support is being provided to Senior Infants in 6 week blocks – Three groups in each class: Two learning support teachers and class teacher.

Mata sa Rang Books supplied to each First and Second Class teacher:

Teaching Number in the Classroom with 4-8 year olds

Teaching Number: Advancing Children’s Skills and Strategies

Priorities for 2013-2014

- Focus on Language

- Oral Mental Starters

- Problem a Day

- Differentiated groups in 6 week blocks in Senior Infants

- Further training in Mata sa Rang

- Three classes teachers implemented the maths programme without  the use of a class textbook